## Slide 1
Town Hall #2 – June 1, 2022
PROJECT OVERVIEW

## Slide 2: Agenda for this meeting
2
Introduction to Design Build Associates
Project overview
What we have accomplished to date
Next steps
Questions and Answers
Notes: 2

## Slide 3: Agenda for this meeting
3
Introduction to Design Build Associates
Project overview
What we have accomplished to date
Next Steps
Questions and Answers
Notes: 3

## Slide 4
Design Build Associates
We are construction managers and consultants and have been in the construction industry for almost 40 years.
We provide our clients with the necessary checks and balances to assure a successful project considering time, quality, and cost objectives.
Our mission is to deliver the best project at the best price, on time and at budget:
  Establishing a proper scope of work
  Prioritizing necessary repairs
  Overseeing project completion in a timely manner

## Slide 5
Village Palos Verdes
180 units
Major Renovation: roofs, siding, windows, more

## Slide 6
Village Palos Verdes
180 units
Major Renovation: roofs, siding, windows, more

## Slide 7
Essex House
25 units
Marina Del Rey
Before

## Slide 8
After

## Slide 9
Indigo
77 units Marina Del Rey
Decking and podium waterproofing
9

## Slide 10
Ziani
168 Condominiums
Newport Coast
10

## Slide 11
11
Las Palmas
405 Condominiums
Mission Viejo

## Slide 13
Past Clients are our best reference
www.dBuild.com
13

## Slide 14: Agenda for this meeting
14
Introduction to Design Build Associates
Project overview
What we have accomplished to date
Next steps
Questions and Answers
Notes: 14

## Slide 15
Bridgeport Project Overview
Damaged wood trim will be replaced.
Balcony wood repairs.
All damaged beams will be replaced, new deck coating installed on all walkways.
New wrought iron must be installed to meet Building Code requirements.
Repairs will be made to the parking garage walls and podium deck to address water intrusion issues.
All previously painted surfaces to be repainted.

## Slide 16
Bridgeport Renovation Project
Pre-Construction Job Process Flowchart June 1, 2022
Discuss HOA financing project. If financing is necessary:
Request proposals and letters of interest from Lenders
Receive Lender Proposals
Select Lender & Complete Finance Package
Identify Key Lenders
Begin defining the Scope of Work and creating a rough cost estimate
Job walk with Account Manager from Behr Paint
Job walk with general contractor Professional Services
Review project documentation
Sign Construction Consulting Agreement
Establish Client Contact and Communication Protocol
Meet the Board and walk the job
Review HOA CC&Rs and reserve Study
Initiate Project
Received preliminary plan sets for walkways, landings and guard rails.
Discovery Testing performed followed by a team site visit for details and specification to be developed.
Paint design development including virtual renderings
January Town Hall #1
DBA Introductions, Project Overview and Update
Discovery Testing approved
Finalize structural engineering plans and submit to the City Plan review
Damaged wood matrix performed and placed into spreadsheet for bid package
All Scope, Design and Specifications Finalized and Approved
Request for Proposal prepared and sent to qualified Bidders
Begin Bidding Process
Bidders identified and qualified
Pre-Bid job walks
Bid Form and Documents completed
Formal job walks during bidding period, Requests for Information answered
Bids received and analyzed, DBA meets with Board to recommend a General Contractor
HOA signs contract with General Contractor – DBA role as Construction Manager specified in contract
General Contractor applies for permits, prepares and mobilizes
FUNDING IN PLACE, PERMIT ISSUED, APPROVALS ATTAINED, LABOR AND MATERIAL IN PLACE
CONSTRUCTION BEGINS
Owner Contractor Agreement negotiated
Legend
Bridgeport HOA
DBA
Team
Lender
Contractor
Beginning of Phase
Critical Path
Project Matrix created , areas of damage identified, destructive testing proposal created
Assessments and mapping of garage leaks.
Completed Task

## Slide 17
Examples of building components that need repair
Trim needs to be repaired and/or replaced.
Siding needs new paint.

## Slide 18
Trim needs to be repaired and/or replaced.

## Slide 19
Wood trim and siding damage
Siding needs new paint

## Slide 20
Facias need repairs

## Slide 21
Stucco damage needs repairs and painting

## Slide 22
Failing structural beams need to be replaced

## Slide 23
Efflorescence on garage walls due to water intrusion

## Slide 24
Water intrusion into the garage and associated damage

## Slide 25: Agenda for this meeting
25
Introduction to Design Build Associates
Project overview
What we have accomplished to date
Next steps
Questions and Answers
Notes: 25

## Slide 26
What we have accomplished to date
Developed scope of work and specifications for the project.
Worked with paint manufacturer to develop the paint specifications.
Completed environmental testing to ensure no lead is present in the existing paint.
Performed balcony inspections.

## Slide 27
What we have accomplished to date (continued)
Completed discovery testing to investigate the extent of damaged beams at the elevated walkways.
Created a “Request for Proposal” detailing the scope of work and the bid documents.
We are currently finalizing the bid documents to issue to qualified contractors for competitive bidding.

## Slide 28
Overview of the Bidding Process
Goal is to deliver the best product at the best price – on time and on budget.
Four qualified general contractors will be competing to perform the work.
The Scope of Work will be clearly defined in a 112-page Request for Proposal.

## Slide 29
Overview of the Bidding Process (continued)
Bids are then compared “apples to apples”.
A contract between the selected contractor and the HOA is prepared for the HOA’s attorney’s review.
Design Build is involved in every step to ensure conformance to the contract.

## Slide 30: Agenda for this meeting
30
Introduction to Design Build Associates
Project overview
What we have accomplished to date
Next Steps
Questions and Answers
Notes: 30

## Slide 31
Next Steps – Information presented at next meeting
Finalized scope of work, including any alternates selected by the Board.
Contractor selected based on competitive bidding.
Structural plans submitted to the City for Plan Review.
Assessment to be presented to membership.
Review budget amount for project and loan.
Financing options will be explained to homeowners.
Ballots will be distributed for voting.

## Slide 32: Agenda for this meeting
32
Introduction to Design Build Associates
Project overview
What we have accomplished to date
Next steps
Questions and Answers
Notes: 32